# Grant Application — Full Proposal (Word variant)

Project title: Strengthening Maternal &amp; Newborn Health in Garissa County

Summary. Amani Health Initiative requests USD 180,000 over 18 months to reduce maternal and
    newborn mortality in three sub-counties through community health promoter (CHP) networks,
    emergency referral support and facility mentorship.

Problem. Garissa's maternal mortality ratio remains far above the national average, driven by
    low skilled-birth attendance, distance to facilities and delayed referral. Displacement from
    the wider region has increased pressure on services.

Objectives. (1) Increase skilled birth attendance from 41% to 60% in the target area.
    (2) Train and equip 120 CHPs. (3) Establish an emergency transport voucher scheme covering
    six health facilities.

Approach. CHP recruitment and training; monthly facility mentorship; a referral voucher
    scheme with local transporters; community dialogue sessions; routine data review.

Beneficiaries. 24,000 women of reproductive age and 6,500 newborns, directly.

Monitoring. Against the attached logframe; monthly CHP reporting; quarterly data review with
    the county health team.

Sustainability. CHPs are integrated into the county community-health strategy; the voucher
    scheme transitions to county co-financing by month 15.