# Quarterly Narrative Progress Report — Q1

Grant: Strengthening Maternal & Newborn Health in Garissa County

Reporting period: Jan–Mar 2026    Prepared by: Fatima Noor, ED

# Progress against objectives

84 of 120 CHPs recruited and trained (70%). The emergency transport voucher scheme launched at four of six facilities. Skilled birth attendance in the target area rose from 41% to 48% this quarter.

# Activities delivered

Three 3-day CHP training cohorts; 512 vouchers issued; monthly mentorship at four facilities; two community dialogue sessions.

# Challenges & mitigation

Seasonal flooding delayed access to two facilities; mitigated by rescheduling mentorship and using boat transport for referrals.

# Finances

USD 41,200 of USD 60,000 tranche 1 expended (69%); full reconciliation attached.

# Next quarter

Complete CHP recruitment; extend vouchers to all six facilities; first data review with the county team.

[TEST DOCUMENT — fictional, for Kuja UAT only]