Table of Contents

# Kuja — Production Deployment Plan

Version: 1.0 · Date: 2026-08-15 · Status: Draft for review Platform: Kuja Grant Management System v5.0.0 (“Kuja Studio”) — multi-tenant Flask + Next.js on Railway Owner: [Programme / Eng lead] · Target launch: [date — after pilot sign-off]

This is the master launch checklist. Work top-to-bottom; each - [ ] is an action with an owner. Sections 1–13 are the plan; Section 14 is the open-risk register; the Appendices are the fill-in checklists you tick on cut-over day. File references (e.g. app/config.py:48) point at where each item lives.

## 0. Executive summary — what “go live” means here

Kuja is one codebase serving four tenants off different hostnames (Kuja Marketplace, NEAR, Proximate/Adeso-Sudan, Saxansaxo/Somalia). The backend (Flask, app/) serves the pre-built Next.js static export (static/nextjs/) and the JSON API; Postgres is the store; Railway hosts it (project clever-cooperation, service web, plus Postgres, Redis, and a near-redirect service). Today the pilot runs on the raw Railway URL web-production-6f8a.up.railway.app with demo (pass123) accounts.

“Launch” = each tenant reachable on its own branded domain, with real accounts, real DNS/TLS/email, the legal & AI-disclosure pages published, the six languages reviewed by native speakers, real-device + accessibility + security certification done, monitoring live, and the demo accounts retired. The sections below cover all of it.

Recommended sequencing: stand up a staging deploy first (there is none today — this is a gap), migrate one tenant (suggest Proximate or NEAR as the first branded go-live since their domains are already documented), certify, then roll the rest.

## 1. Environments & release management

- Create a staging environment on Railway (separate service + Postgres) that mirrors prod config. There is currently only prod; every change is tested against pilot-on-prod, which is risky at launch scale.

- Confirm the branch→deploy flow: push to main → Railway auto-deploys → poll GET /api/version for the expected build SHA. Document the expected turnaround (~1–3 min).

- Frontend build gotcha (critical): Railway does not rebuild the Next.js frontend. The committed static/nextjs/ export is what ships. Any frontend change must be built (npm run build in frontend/) and the regenerated static/nextjs/ committed. The CI gate .github/workflows/frontend-build-sync.yml (runs frontend/scripts/verify-built.js) fails the build if the export drifts from source — keep it green.

- Adopt a release/tag convention and keep docs/PHASE_*_RELEASE_NOTES.md updated per release.

- Define a deploy freeze window policy around launch (no non-hotfix deploys 48h pre/post launch).

- Add a post-deploy verification script that polls /api/version for the expected SHA and runs the smoke gate (today regression.py polls /api/health but nothing asserts the deployed SHA).

## 2. Domains, DNS & TLS

The host→tenant mapping lives in app/models/network.py::Network.resolve_from_host (matches host_aliases, then subdomain-prefix vs slug, then falls back to the kuja default). Per-tenant DNS steps already exist in docs/NEAR_DNS_SETUP.md and docs/PROXIMATE_DOMAIN_SETUP.md — reuse and extend them.

Target domains (confirm final with the client):

| Tenant (slug) | Planned production host(s) | Code host_aliases today | Status |
| --- | --- | --- | --- |
| Kuja Marketplace (kuja) | [e.g. app.kuja.org] | (none — catch-all) | ⚠ pick + add alias |
| NEAR (near) | near.kuja.org, app.near.ngo | already set | DNS doc exists |
| Proximate (proximate) | proximate.kuja.org, proximate.adesoafrica.org | already set | DNS doc exists, live once switched |
| Saxansaxo (saxansaxo) | saxansaxo.kuja.org, sclr.kuja.org | already set | DNS doc exists |

Per domain: - [ ] Add the custom domain in Railway (railway domain add <host> on service web) and complete verification (TXT _railway-verify.<sub> + CNAME to the Railway target). Watch the known gotcha (doubled TXT prefix / stuck verification — see the DNS docs). - [ ] Confirm TLS: Railway auto-provisions Let’s Encrypt; verify the cert covers the exact host, auto-renews, and HSTS is honored (HSTS is set in prod by app/middleware.py::add_security_headers). - [ ] Decide apex vs subdomain and set up www→apex (or apex→www) redirect; apex domains need ALIAS/ANAME or a redirect service (the repo already has a near-redirect service pattern). - [ ] Add the new host to the network’s host_aliases in the DB/seed (app/__init__.py seed block) so the tenant resolves. - [ ] CORS: allowed origins are locked to the base Railway origin only (app/__init__.py:63). Add every real tenant domain to the CORS_ORIGINS env var (comma-separated) or logins/API calls from the branded domain will fail. - [ ] WebAuthn / passkeys: the RP ID/origin default to the base Railway host (app/services/webauthn_service.py:46). Set WEBAUTHN_ORIGIN and WEBAUTHN_RP_ID to the launch domain, or passkeys won’t validate. (For multi-domain, WebAuthn RP ID must be the registrable parent domain shared by the tenants.) - [ ] Reserve role/support addresses on the domain: support@, privacy@, security@, noreply@ (see §7 legal + §10 email). - [ ] Update hard-coded base-URL defaults where a tenant needs them: KUJA_PUBLIC_HOST, KUJA_PUBLIC_BASE_URL, PROXIMATE_PUBLIC_BASE_URL (used for VC/report public links).

## 3. App icon, PWA manifest & installer

Kuja is an installable PWA (no native app store build today). Assets follow the frontend/public/tenants/<slug>/ convention; the runtime swaps icon/manifest/theme per tenant in frontend/src/components/network-provider.tsx.

- Per-tenant icon set exists for all four tenants (favicon.ico, favicon-32.png, icon-180.png apple-touch, icon-192.png, icon-512.png, manifest.webmanifest). Verify each is the final brand art, not placeholder, at all sizes; add a maskable 512 (Android adaptive) and confirm icon-180 is square with safe padding for iOS.

- Confirm each tenant’s manifest.webmanifest has correct name, short_name, theme_color (brand hex), background_color, display: standalone, start_url: /dashboard, and dir/lang (Proximate = rtl/ar).

- Install prompt (frontend/src/components/shared/pwa-install-banner.tsx, captures beforeinstallprompt) — test the banner shows on Android/Chrome and the iOS “Add to Home Screen” hint path works (iOS gives no beforeinstallprompt).

- Splash screens: generate iOS launch images (or accept default) per tenant theme.

- Service worker (frontend/public/sw.js) — verify offline caching + cache-busting on new deploys (stale-SW is a classic launch bug); confirm the IndexedDB offline outbox syncs when back online.

- Confirm theme-color meta, address-bar color, and standalone status bar look right per tenant on real devices.

- Decide whether any tenant needs a true native wrapper (TWA for Play Store / Capacitor) — out of scope for v1 unless the client requires an app-store listing; note as a follow-up.

## 4. Infrastructure & configuration

Runtime: Procfile/railway.json → gunicorn --workers 4 --threads (4–8) --timeout 180 --worker-class gthread --max-requests 1000 --preload server:app, after pre_deploy.py + flask db upgrade. ProductionConfig.init_app fails fast if SECRET_KEY is unset/default (app/config.py:48).

- Postgres: confirm plan/sizing; connection pool is pool_size=10, max_overflow=15, pool_recycle=300 (app/config.py:57). Enable automated backups + document restore drill (see §9). Set PITR / retention to meet the agreed RPO.

- Redis: provision and set REDIS_URL / RATE_LIMIT_REDIS_URL. Required at multi-worker scale because (a) WebAuthn re-auth tokens are stored in-process today (webauthn_service.py) and (b) rate-limit policies want a shared store. Without Redis, passkey re-auth and rate limits behave inconsistently across the 4 workers.

- Secrets management: set every required env var in Railway (see Appendix A). Rotate any secret that has ever been in a demo/pilot context. Never commit secrets.

- SEED_PROXIMATE_ON_BOOT=false before real users (confirmed already false on prod — keep it).

- CRON_SECRET must be set explicitly (else it auto-generates per-process and multi-worker crons break) — the 12 scheduled GitHub Actions authenticate with it.

- File storage: if using object storage, set S3_* (S3_ENDPOINT/ACCESS_KEY/SECRET_KEY/BUCKET/REGION); otherwise confirm UPLOAD_FOLDER is on a persistent volume (Railway ephemeral FS loses uploads on redeploy). Decide + document.

- AI budget & keys: set ANTHROPIC_API_KEY; confirm the per-tenant/user AI cost ceiling (KUJA_AI_BUDGET_USD_30D, default 250) and concurrency (KUJA_USER_AI_CONCURRENT) are right for launch volume. Confirm the production model ID is current (no stale claude-* strings).

- Health/readiness: wire uptime checks to GET /api/health, GET /api/ready (DB SELECT 1), GET /api/version (build SHA + frontend_build), GET /api/admin/canary (external deps).

- Scaling & limits: confirm worker count vs Railway CPU/memory (prior load test showed the app is render/CPU-bound at ~6 rps, not connection-bound); set autoscaling or a known ceiling; MAX_CONTENT_LENGTH=16MB + the WSGI oversized-upload guard are in place.

- Time & locale: confirm server TZ is UTC (timestamps are serialized UTC-aware after the recent iso_utc fix).

- Refresh OPERATIONS.md — it is stale (says v3.x, gevent, single worker, old model). Bring it to v5.0.0 / 4-worker gthread reality as the on-call runbook.

## 5. Security & data protection

Strong surface already (RBAC, DB-backed lockout, hash-chained audit, 2FA, WebAuthn, sanctions screening, CSP). Launch hardening:

- Retire demo accounts: run retire_demo_accounts.py --confirm on prod to deactivate + randomize every pass123 account before branded go-live (they’re re-enabled now for pilot QA). Verify pass123 returns 401.

- Enforce admin 2FA: set KUJA_ENFORCE_ADMIN_2FA=true (today it’s soft/nag). Ensure all admin/OB users have enrolled TOTP or a passkey first.

- Password reset gap: there is no self-service password reset (OPERATIONS.md) — only admin/DB reset + the forced must_change_password flow. Decide whether launch needs a self-service reset (email-token) flow, or document the admin-reset SOP for support.

- Redis for WebAuthn (see §4) so passkey re-auth is reliable.

- CSP hardening: current script-src allows 'unsafe-inline' (flagged TODO in middleware.py). Move to nonce/hash-based CSP before launch if the client’s security review requires it.

- Secret rotation on launch: SECRET_KEY, ANTHROPIC_API_KEY, Twilio, SendGrid, DB creds, CRON_SECRET, VC signing key. Document rotation cadence.

- RBAC / tenant-isolation regression: run the negative-authz + cross-tenant scoping tests (test_trust_tenant_guard.py, scope_* coverage) and confirm no persona can see another tenant’s or another role’s data.

- Audit-chain integrity: run verify() on the prod chain; confirm per-tenant network_id stamping; set KUJA_AUDIT_RETENTION_DAYS per policy.

- Sanctions/DD: set OPENSANCTIONS_API_KEY + SAM_GOV_API_KEY; confirm the rescreening scheduler runs on exactly one worker (RESCREENING_SCHEDULER).

- Data classification & residency: document where prod data physically lives (Railway region) vs where subjects are (Kenya, Somalia, Sudan, South Africa). This drives the POPIA/Kenya-DPA analysis in §7. Consider region pinning if required.

- Encryption: confirm TLS in transit everywhere and encryption-at-rest for Postgres + object storage.

- Penetration test / security review (see §9).

- Backups are encrypted and access-controlled; test restore.

- Incident response & responsible disclosure: publish security@ + a coordinated-disclosure policy; document P0–P3 escalation (OPERATIONS.md has a draft).

## 6. Legal & policy documents ⚠ BIGGEST GAP — none exist today

There are no privacy, terms, cookie, consent, or AI-disclosure pages in the app (a GDPR right-to-be-forgotten admin endpoint exists, but nothing user-facing). Because the platform handles NGO/beneficiary personal data, runs AI-assisted scoring/decisions, and (in Proximate) moves funds, these are launch blockers, not nice-to-haves. Draft with counsel; then build the pages + acceptance flow.

Documents to produce & publish (per tenant where branding/entity differs): - [ ] Privacy Policy — data collected, purposes, legal basis, retention, sub-processors, subject rights, contact. Cover GDPR (EU donors/staff), Kenya Data Protection Act 2019, South Africa POPIA (Adeso is SA-registered), and any Somalia/Sudan considerations. - [ ] Terms of Service / Platform Use Agreement — separate donor vs NGO vs reviewer terms where obligations differ. - [ ] AI & Automated Decision-Making Notice — disclose that AI (Anthropic) assists scoring/guidance, that a human makes the final funding decision, the right to explanation/appeal (the app already has an appeal flow + provenance UI to point to), and data handling by the AI sub-processor. - [ ] Cookie / Local-storage notice + consent banner — the app uses cookies (session) + localStorage (PWA, dismissals); provide a notice and, if targeting EU, a consent mechanism. - [ ] Data Processing Agreement (DPA) template for donor/partner organizations (Kuja/Adeso as processor or controller as appropriate). - [ ] Sub-processor list — Anthropic (AI), Twilio (SMS/WhatsApp), Meta (WhatsApp), SendGrid (email), Railway (hosting), OpenSanctions/SAM.gov (screening), any object storage. Publish + keep current. - [ ] Acceptable Use Policy (esp. AI/content generation). - [ ] Data Retention & Deletion Policy (ties to KUJA_AUDIT_RETENTION_DAYS and the RTBF endpoint). - [ ] Safeguarding / PSEA statement — mandatory in humanitarian contexts (vulnerable beneficiaries, Sudan/Somalia). - [ ] AML / sanctions-screening statement — for Proximate disbursements (hawala/mobile-money FSPs); document the KYC/DD and sanctions process. - [ ] Accessibility statement (WCAG 2.1 AA target; see §9). - [ ] Responsible-disclosure / security policy (from §5). - [ ] Consent-at-signup / terms-acceptance flow in the app (record acceptance + version + timestamp in the audit chain). - [ ] Confirm entity, jurisdiction, and governing law per tenant with the client/legal.

## 7. Localization & translation certification

Six languages ship: English, Somali, Swahili, Spanish, French, Arabic (Arabic = RTL). Strings live in frontend/src/i18n/<lang>.json (flat dotted keys); there are also server-side generated strings (title_key/params in notifications/audit — see docs/i18n_review_targets.md).

- Reviewer workbooks produced — docs/i18n-review/Kuja_i18n_review_<lang>.xlsx (+ copies in Downloads\Latest Kuja files\), one per language, with instructions, the full string table (English source, current translation, placeholders to preserve, MISSING/SAME-as-English flags, editable correction columns), and a glossary tab. Generated by docs/i18n-review/generate_review_workbooks.py.

- Assign a native speaker per language and set a return date. Prioritise the rows flagged MISSING (19 per language — English-only keys) and SAME AS ENGLISH (fr 379, es 300, sw 281, so 279, ar 23 — likely untranslated).

- Re-import corrected strings back into the JSON (add a small importer that reads the workbook’s “corrected” column and writes <lang>.json), rebuild the frontend, and run the i18n parity gate.

- Server-side strings: ensure the title_key/param strings and any app/utils/i18n.py-loaded backend strings are in the review set (they’re not all in the frontend JSON).

- RTL QA (Arabic): verify layout mirroring, number/date direction, mixed LTR (names/URLs) rendering, and the Arabic PDF pipeline (arabic-reshaper + python-bidi).

- Locale formatting: dates, numbers, currency per locale; confirm no hard-coded English date/number formats.

- Native-speaker sign-off recorded per language (part of go/no-go).

## 8. Testing & certification

Existing automation to keep green: smoke_test.py (pre-deploy gate, ~14 tests), regression.py (+ --browser Playwright), browser_test.py, mobile_test.py (docs/MOBILE_TESTING.md), test_pilot_hygiene.py (cross-persona live probe), and the GitHub Actions (smoke.yml, regression.yml, health-monitor.yml every 5 min, frontend-build-sync.yml, 12 cron jobs).

Certifications required before launch: - [ ] Real-device mobile testing — a physical matrix, not just emulator. Minimum: low-end Android (Chrome), mid Android, iPhone (Safari), small viewport 360×800, plus a tablet. Test: install-as-PWA, offline/airplane-mode capture + sync, slow-3G/low-bandwidth (Global-South target), photo/voice capture, RTL on Arabic. (Note: the copilot-rail mobile-overflow fix shipped but its live 360×800 pixel-check is still pending.) - [ ] Accessibility (WCAG 2.1 AA) — automated (axe) + manual screen-reader pass (VoiceOver/TalkBack), keyboard-only nav, focus states, colour contrast, RTL, and the skip-to-content link. Publish the accessibility statement (§6). - [ ] Native-speaker translation review — the six workbooks (§7) signed off. - [ ] Security penetration test — external test of authz/tenant isolation, session/CSRF, file upload, rate limits, WebAuthn, injection; remediate before launch. - [ ] Load / performance test — validate expected concurrent users against the ~6 rps CPU-bound baseline; decide worker/instance count; test AI-endpoint latency + budget behavior under load. - [ ] Cross-browser — Chrome, Safari, Firefox, Edge (desktop + mobile). - [ ] UAT sign-off — per-tenant end-to-end business flows with the client (docs/UAT_FIXTURES.md, scripts/certify_uat_remaining.py). - [ ] Data migration / backup-restore drill — restore a prod backup into staging and verify integrity + audit chain. - [ ] Email/SMS/WhatsApp deliverability test end-to-end (see §10). - [ ] Deploy-verification test — confirm /api/version reports the expected SHA + frontend_build post-deploy.

## 9. Messaging & email deliverability

- Email (SendGrid): Railway blocks outbound SMTP, so use the SendGrid Web API path (app/services/email_service.py prefers it). Set SENDGRID_API_KEY, MAIL_FROM (e.g. noreply@adesoafrica.org), MAIL_FROM_NAME. Today email is log-only in prod — this must be configured or no NGO/donor notifications go out.

- Email authentication DNS: add SPF, DKIM (SendGrid domain authentication), and DMARC records for the sending domain; verify sender domain; test inbox placement (not spam) to Gmail/Outlook.

- WhatsApp/Twilio: sender +254705529285 is live; 8 templates are pending Meta approval (endorsement_invite, endorsement_reminder, report_ack, report_reminder, disbursement_notify, outcome_reminder, partner_cleared, round_activated — EN+AR). Get them approved, then wire the template SIDs into messaging_service.py. Confirm TWILIO_* + WHATSAPP_* env vars and webhook verification (docs/WEBHOOK_VERIFICATION.md, WHATSAPP_VERIFY_TOKEN).

- SMS fallback (TWILIO_FROM_NUMBER) tested.

- Messaging consent/opt-in — WhatsApp/SMS to beneficiaries needs documented opt-in; align with the privacy policy.

- Web push (VAPID) — if used at launch, set VAPID_PUBLIC_KEY/PRIVATE_KEY/SUBJECT and test.

## 10. Monitoring, alerting & observability

- Uptime/health — health-monitor.yml already probes /api/health + /api/network/current every 5 min (alerts via GitHub email). Add a paging channel (PagerDuty/Teams/email that’s actually watched) and a public status page.

- Error tracking — set SENTRY_DSN (Sentry is wired) and confirm errors flow with release tagging.

- Synthetic monitoring — synthetic_monitor.py login probes are opt-in via KUJA_SYN_* creds; decide whether to run them against a dedicated monitor account (not pass123).

- AI cost/quality — watch the AI budget ceiling + telemetry dashboards; alert on cost spikes and AI failure-rate.

- Audit-chain integrity monitor — schedule periodic verify().

- Log retention & access — define retention; ensure PII isn’t over-logged; restrict log access.

- DB & Redis metrics — connection saturation, slow queries, memory.

## 11. Backups, disaster recovery & business continuity

- Define RPO/RTO with the client.

- Automated Postgres backups (a weekly-backup cron exists) + verified restore drill into staging.

- Object-storage/upload backups (if S3) or persistent-volume snapshot policy.

- Runbook for full recovery (recreate service, restore DB, restore uploads, re-point DNS).

- Config/secret backup (secure) so a service can be rebuilt.

- Rollback plan per deploy (redeploy previous build; railway redeploy is the documented recovery — see health-monitor doc).

## 12. Launch runbook (cut-over day)

Pre-launch (T-1 week): - [ ] All §1–11 checkboxes closed or explicitly risk-accepted. - [ ] Legal pages published; terms-acceptance flow live. - [ ] Translations signed off + re-imported + deployed. - [ ] Real accounts provisioned (provision_users.py); forced-password-change on first login verified. - [ ] Demo pass123 accounts retired; admin 2FA enforced. - [ ] DNS/TLS/CORS/WebAuthn for the launch domain(s) verified; email + WhatsApp deliverability green. - [ ] Backups + monitoring + on-call confirmed.

Go / No-Go review: sign-off from Eng, Product, Client, Legal, Security.

Cut-over: - [ ] Deploy the release; confirm /api/version SHA + frontend_build. - [ ] Flip DNS to the tenant domain (low TTL beforehand). - [ ] Run the smoke gate + test_pilot_hygiene.py against the live domain. - [ ] Manual cross-persona click-through per tenant (donor/NGO/reviewer/OB) + mobile install. - [ ] Confirm a test email + WhatsApp actually arrive.

Post-launch (T+0 to T+72h): - [ ] Watch Sentry, health-monitor, AI cost, DB metrics closely. - [ ] Support channel staffed; known-issues list ready. - [ ] Daily standup on launch health; hotfix path warm.

Rollback: railway redeploy to the previous good build; if DNS-related, revert DNS; communicate status.

## 13. Roles, ownership & timeline

- Fill a RACI for each section owner: Eng lead, DevOps, Product, Client/Programme, Legal/DPO, Security, Localization coordinator, Support lead.

- Put dates against Sections 2–12 working back from the target launch; the long-poles are usually legal drafting, Meta template approval, native-speaker review turnaround, and pen-test remediation — start those first.

## 14. Open risks / gaps register (start these now)

| # | Gap / risk | Impact | Section |
| --- | --- | --- | --- |
| 1 | No legal/privacy/AI-disclosure pages | Launch blocker (compliance) | §6 |
| 2 | No staging environment | Risky changes tested on prod | §1 |
| 3 | CORS locked to base Railway origin; WebAuthn origin/RP unset for tenant domains | Logins/passkeys break on branded domains | §2 |
| 4 | WebAuthn re-auth tokens + rate limits in-process → need Redis | Inconsistent auth/limits across workers | §4/§5 |
| 5 | Email is log-only (SMTP blocked); SendGrid + SPF/DKIM/DMARC not set | No notifications reach users | §9 |
| 6 | 8 WhatsApp templates pending Meta approval; SIDs not wired | Proximate messaging can’t send | §9 |
| 7 | No self-service password reset | Support burden / lockouts | §5 |
| 8 | Demo pass123 accounts active | Security exposure at launch | §5 |
| 9 | Upload persistence on Railway ephemeral FS (unless S3/volume) | Data loss on redeploy | §4 |
| 10 | OPERATIONS.md stale (v3.x) | Wrong on-call info | §4 |
| 11 | CSP allows 'unsafe-inline' scripts | Weaker XSS posture | §5 |
| 12 | Mobile 360×800 fix not yet pixel-verified on a device | UI regression risk | §8 |
| 13 | No app-store/native wrapper decision | Client expectation mismatch | §3 |
| 14 | Data residency vs POPIA/Kenya-DPA not analysed | Compliance | §5/§6 |

## Appendix A — Environment variable checklist (set in Railway)

Required for any launch: DATABASE_URL, SECRET_KEY (strong, non-default — app fails to boot otherwise), CORS_ORIGINS (all tenant domains), CRON_SECRET, ANTHROPIC_API_KEY, SENDGRID_API_KEY + MAIL_FROM + MAIL_FROM_NAME, REDIS_URL, WEBAUTHN_ORIGIN + WEBAUTHN_RP_ID, SEED_PROXIMATE_ON_BOOT=false.

Security/limits: KUJA_ENFORCE_ADMIN_2FA=true, RATE_LIMIT_*, AUTH_ABUSE_SLO_*, GRANT_LICENSING_ENFORCED (per commercial model).

Screening: OPENSANCTIONS_API_KEY, SAM_GOV_API_KEY, RESCREENING_SCHEDULER, RESCREENING_INTERVAL_HOURS.

Messaging: TWILIO_ACCOUNT_SID, TWILIO_AUTH_TOKEN, TWILIO_FROM_NUMBER, TWILIO_WA_FROM, WHATSAPP_PHONE_NUMBER_ID, WHATSAPP_BUSINESS_ACCOUNT_ID, WHATSAPP_ACCESS_TOKEN, WHATSAPP_APP_SECRET, WHATSAPP_VERIFY_TOKEN.

AI tuning: ANTHROPIC_WEB_SEARCH, KUJA_AI_BUDGET_USD_30D, KUJA_USER_AI_CONCURRENT, WHISPER_API_KEY/WHISPER_MODEL/WHISPER_API_URL.

Storage/infra: S3_ENDPOINT/S3_ACCESS_KEY/S3_SECRET_KEY/S3_BUCKET/S3_REGION (or persistent UPLOAD_FOLDER), TASK_RUNNER_WORKERS, VAPID_PUBLIC_KEY/VAPID_PRIVATE_KEY/VAPID_SUBJECT, SENTRY_DSN, KUJA_PUBLIC_HOST/KUJA_PUBLIC_BASE_URL/PROXIMATE_PUBLIC_BASE_URL, KUJA_VC_SIGNING_KEY_HEX, KUJA_AUDIT_RETENTION_DAYS.

## Appendix B — Domain & DNS checklist (per tenant)

| Step | kuja | near | proximate | saxansaxo |
| --- | --- | --- | --- | --- |
| Final host(s) confirmed | ☐ | ☐ | ☐ | ☐ |
| Railway domain added + verified (TXT+CNAME) | ☐ | ☐ | ☐ | ☐ |
| TLS cert issued + HSTS | ☐ | ☐ | ☐ | ☐ |
| host_aliases updated in DB/seed | ☐ | ☐ | ☐ | ☐ |
| Added to CORS_ORIGINS | ☐ | ☐ | ☐ | ☐ |
| WebAuthn origin/RP covers host | ☐ | ☐ | ☐ | ☐ |
| Email SPF/DKIM/DMARC on domain | ☐ | ☐ | ☐ | ☐ |
| www/apex redirect | ☐ | ☐ | ☐ | ☐ |

## Appendix C — Device / accessibility test matrix

| Device / target | Install PWA | Offline+sync | Slow-3G | Photo/voice | RTL (ar) | Screen reader |
| --- | --- | --- | --- | --- | --- | --- |
| Low-end Android (Chrome) | ☐ | ☐ | ☐ | ☐ | ☐ | ☐ (TalkBack) |
| Mid Android (Chrome) | ☐ | ☐ | ☐ | ☐ | ☐ | ☐ |
| iPhone (Safari) | ☐ | ☐ | ☐ | ☐ | ☐ | ☐ (VoiceOver) |
| 360×800 small viewport | ☐ | — | ☐ | — | ☐ | — |
| Tablet | ☐ | — | — | — | ☐ | — |

## Appendix D — Legal document checklist

Privacy Policy ☐ · Terms of Service (donor/NGO/reviewer) ☐ · AI & Automated-Decision Notice ☐ · Cookie/consent notice + banner ☐ · DPA template ☐ · Sub-processor list ☐ · Acceptable Use ☐ · Data Retention & Deletion ☐ · Safeguarding/PSEA ☐ · AML/sanctions statement ☐ · Accessibility statement ☐ · Responsible disclosure ☐ · In-app terms-acceptance flow ☐.

References throughout point at the codebase (e.g. app/config.py, app/middleware.py, frontend/public/tenants/, docs/NEAR_DNS_SETUP.md, docs/PROXIMATE_DOMAIN_SETUP.md, docs/OPS_WHATSAPP_TWILIO_SETUP.md, docs/MOBILE_TESTING.md, docs/i18n_review_targets.md). Update this plan as items close.