## 0. Read me
Proximate Fund — End-to-End UAT Test Pack (July 2026)
What this is
A complete user-acceptance test of the Proximate console on live production. It walks every persona (Oversight Body, Community Endorser, Partner, Donor, Platform Admin, and the anonymous public surfaces) through every workflow end to end: grant intake, round setup, partner nomination, community endorsement, due diligence, disbursement with co-signing, partner reporting by token link, the donor report package with AI compile, publication, outcome attestation, grievances, panel voting, audit chain and transparency.
Environment
URL: https://web-production-6f8a.up.railway.app
ALWAYS log in via this exact link: https://web-production-6f8a.up.railway.app/login/?network=proximate
(The plain /login page clears the Proximate context — if you ever see marketplace branding, re-open the link above.) If proximate.kuja.org has gone live on your network, you can use it instead and drop the ?network=proximate part.
Recommended browser: Chrome or Edge, normal window ~1280px wide. Where a case says 'incognito', use a private window so you are logged out.
Ground rules — read before starting
1. This is PRODUCTION. The tenant contains one REAL funding round: 'Blue Nile' (round 9), with real partners and files. Do not open actions, approve, reject, vote, or create anything against it. All test cases use the UAT round you create in case B-02, or demo round 8.
2. Disbursement #24 is a deliberately flagged QA fixture. Look, but never resolve/unflag it (case E-10).
3. Prefix everything you create with 'UAT' — rounds, partners, grievances, notes. That is how we clean up afterwards.
4. Sample files live in the Kuja_UAT_Assets folder that was shared with this workbook. Cases reference them by exact file name.
5. AI steps (extraction, compile, web-check) cost tokens — run them once per case, not repeatedly.
6. Some values are created during the run (round ID, partner ID, disbursement IDs). Write them into the 'Runtime values' table on the next sheet as you go — later cases refer to them as {R}, {P}, {D1}, {D2}.
How to run
Work the sheets in order 1 → 9; within a sheet, run cases top to bottom (later cases depend on earlier ones). Sheets 1 and 9 can be run by anyone at any time; sheets 2-8 form one continuous story and are best run by one pair (an 'OB' tester and a 'second device' tester for the public/token pages).
Mark each case Pass / Fail / Blocked / N/A in the Result column. For any Fail, add a row on the 'Defect log' sheet with a screenshot reference. A case fails if the expected result does not happen, if you see raw internal codes (e.g. dd_clear, pending_cosign) anywhere, if anything appears in the wrong language, or if you see an error page.
Estimated effort: sheets 1-9 ≈ 6-8 hours for a pair of testers, comfortably one day.

## Accounts & fixtures
Persona | Email / access | Password | Notes
Oversight Body (OB) #1 | ob@proximate.org | pass123 | Primary operator account. English UI. Runs most cases.
Oversight Body (OB) #2 | ob2@proximate.org | pass123 | Second OB seat — needed for co-signing disbursements over $10,000 (case E-04).
Donor | uat.donor@proximate.org | Uat-Proximate-26 | UAT Donor Foundation. Sees demo round 8 + any round it funds (the round you create in B-02). Created for this UAT on 19 July 2026.
Community Endorser | fatima@amani.org | pass123 | Approved endorser — runs the endorsement wizard (C-06).
Platform Admin | admin@kuja.org | pass123 | Kuja platform admin. Used for the audit-chain and cross-tenant checks. Log in via the same ?network=proximate link.
Partner | — no login — | — | Partners are exercised through the public token links (report page, outcome page) and the public nomination form. No account needed.
Read-only observer | — held by Idiris — | — | Database-flagged read-only account for leadership walk-throughs. Optional case A-10; credentials are not distributed in this pack.
Sample files (Kuja_UAT_Assets folder)
UAT_Grant_Agreement_UATDonor.pdf | Grant agreement for the AI extraction wizard (B-01). Contains: UAT Emergency Response Grant 2026, USD 50,000, 1 Aug 2026 – 31 Jan 2027.
UAT_PIF_Amal_Relief.pdf | Partner Information Form for 'Amal Relief Initiative (UAT)' — used in DD (D-01).
UAT_Registration_Certificate_Amal.pdf | Registration certificate attachment for PIF intake (D-01).
UAT_Leadership_List_Amal.pdf | Three leaders + two board members for leadership screening (D-04).
UAT_Panelist_CV_Halima.pdf | CV for panel candidate 'Halima Adam Koko' (B-07).
UAT_Evidence_Photo_1.jpg / _2.jpg / _3.jpg | Orange/blue/green labelled test photos — evidence uploads (D-05, F-03).
UAT_Voice_Note.wav | 2.5-second tone clip — voice answer upload (F-02). Transcription may be empty; that is expected.
UAT_Evidence_Video.mp4 | 4-second clip — video evidence upload and playback (F-03).
Runtime values — fill these in as you create them
{R} | Round ID of 'UAT Round — July 2026 (Team)' | created in B-02
{P} | Partner ID of 'Amal Relief Initiative (UAT)' | created in C-01
{D1} | Small disbursement ID (USD 4,500) | created in E-01
{D2} | Large disbursement ID (USD 12,000) | created in E-03
{PKG} | Report package ID for round {R} | created in G-01
Existing fixtures you will see (do not modify): demo round 8 'UAT Round P0-20260708-53984' with 2 published report packages; REAL round 9 'Blue Nile' — hands off; flagged disbursement #24 — hands off.

## 1. Access & security
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
A-01 | OB | ob@proximate.org / pass123 | None | 1. Open https://web-production-6f8a.up.railway.app/login/?network=proximate 2. Log in. 3. Look at the left sidebar and the top of the page. | OB #1 credentials | Login succeeds and lands on the Proximate operator dashboard (/proximate/admin/). Sidebar is grouped Workspace / Operations / Governance. Proximate branding (orange), not Kuja marketplace. No marketplace menu items (Grants marketplace, Applications, etc.).
A-02 | OB | ob@proximate.org (already logged in) | A-01 done | 1. Open Settings (sidebar). 2. In Preferences, switch Language to العربية (Arabic). 3. Look at the dashboard and one register page. 4. Switch back to English. | Language: Arabic | Whole console flips to right-to-left: sidebar on the right, Arabic labels everywhere, no mixed left-over English fragments in navigation. Switching back restores English/LTR.
A-03 | Donor | uat.donor@proximate.org / Uat-Proximate-26 | None | 1. Open https://web-production-6f8a.up.railway.app/login/?network=proximate in a fresh browser/profile. 2. Log in as the donor. 3. Review what is visible. | Donor credentials | Lands on the donor portal (/proximate/donor/). Sees round 8 'UAT Round P0-20260708-53984' (and, after B-02, the UAT round). NO operator navigation — no Partners register, no Disbursements admin, no endorser approvals.
A-04 | Endorser | fatima@amani.org / pass123 | None | 1. Open https://web-production-6f8a.up.railway.app/login/?network=proximate in a fresh browser/profile. 2. Log in. 3. Review what is visible. | Endorser credentials | Lands on the endorser surface (/proximate/endorse/) — a simple inbox of partners to endorse. No operator console, no donor portal.
A-05 | Donor (negative) | uat.donor@proximate.org | Logged in as donor | 1. Paste https://web-production-6f8a.up.railway.app/proximate/admin/ into the address bar. 2. Then try https://web-production-6f8a.up.railway.app/proximate/admin/partners/. | Direct URLs | Both pages refuse: redirect away or show an access-denied state. No operator data (partner names, counts) flashes on screen even briefly.
A-06 | Endorser (negative) | fatima@amani.org | Logged in as endorser | 1. Paste https://web-production-6f8a.up.railway.app/proximate/disbursements/ into the address bar. 2. Then try https://web-production-6f8a.up.railway.app/proximate/rounds/. | Direct URLs | Refused the same way — no disbursement or round data visible.
A-07 | Anonymous (negative) | — logged out — | Use an incognito window | 1. Open https://web-production-6f8a.up.railway.app/proximate/admin/ while logged out. | Direct URL | Redirected to the login page. No console content is shown before the redirect.
A-08 | OB | ob@proximate.org | A-01 done | 1. On the dashboard, press Ctrl+K (Cmd+K on Mac). 2. Type 'partners'. 3. Also confirm no marketplace 'What's new' banner appears anywhere in the console. | — | Command palette lists Proximate destinations only (Partners register etc.) — no Kuja marketplace pages. Selecting navigates. No marketplace banner on any Proximate page.
A-09 | OB | ob@proximate.org | Logged in | 1. Log out (Settings → sign out). 2. Press the browser Back button twice. | — | Returned to login. Back button does not reopen console pages with data (a cached shell that redirects to login is acceptable).
A-10 | Read-only observer (optional) | Idiris's read-only account | Credentials held by Idiris | 1. Log in with the read-only account. 2. Open any partner and try to save any change (e.g. add a note or method). | Any edit attempt | Every screen the role allows opens normally, but every save/submit is rejected with a clear 'this account is read-only' message. Nothing is persisted.
A-11 | Platform Admin | admin@kuja.org / pass123 | None | 1. Log in via https://web-production-6f8a.up.railway.app/login/?network=proximate. 2. Open https://web-production-6f8a.up.railway.app/admin/audit-chain/. 3. Expand any recent row. | — | Audit chain renders two levels: collapsed rows read like 'Report package #3 — created — by … — when'; expanding shows hashes + payload JSON. Any token values are redacted (shown as token:xxxx…).
A-12 | Any (negative) | ob@proximate.org with wrong password | None | 1. Open https://web-production-6f8a.up.railway.app/login/?network=proximate. 2. Enter ob@proximate.org with password 'wrongpass' and submit. 3. Then log in with the correct password. | wrongpass | Wrong password shows a clear, non-technical error and no partial login. Correct password then works.

## 2. Round & grant setup
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
B-01 | OB | ob@proximate.org | Logged in | 1. Open https://web-production-6f8a.up.railway.app/proximate/grants/. 2. Choose to add/upload a grant and select UAT_Grant_Agreement_UATDonor.pdf. 3. Wait for the AI extraction wizard. 4. Review the extracted fields, correct anything wrong, confirm/save. | UAT_Grant_Agreement_UATDonor.pdf | Wizard pre-fills from the PDF: title 'UAT Emergency Response Grant 2026', amount USD 50,000, period 1 Aug 2026 – 31 Jan 2027. After confirming, the grant appears as a card showing the funding period. (Minor extraction misses are OK if editable — note them.)
B-02 | OB | ob@proximate.org | B-01 done | 1. Open https://web-production-6f8a.up.railway.app/proximate/rounds/. 2. Click New round. 3. Trigger: donor commitment. Donor: select 'UAT Donor Foundation' from the dropdown. 4. Title: 'UAT Round — July 2026 (Team)'. Envelope: USD 20,000. 5. Create, then note the round ID from the page URL into 'Runtime values' as {R}. | Title, donor, envelope as in steps | Round is created and opens as a detail page with tabs and a journey strip showing the current stage. It appears in the rounds register.
B-03 | OB | ob@proximate.org | B-02 done | 1. On round {R}, click through all tabs. 2. Check the journey strip at the top. | Round {R} | Five tabs render without errors. The journey strip highlights the current stage and shows what comes next in plain language.
B-04 | OB | ob@proximate.org | Logged in | 1. Open https://web-production-6f8a.up.railway.app/proximate/crisis-selector/. 2. Add a manual crisis signal: severity High, note 'UAT signal — Blue Nile access constraint (test entry)'. 3. Save and review the list. | Signal note as in steps | Signal saves and appears in the list with a severity band (colour-coded). The page explains its purpose (feeding round triggers) in a header. Do NOT start a round from here.
B-05 | OB | ob@proximate.org | B-02 done | 1. In the rounds register, click a status filter chip (e.g. Active/Draft). 2. Copy the page URL, open it in a new tab. | — | The list filters; the URL contains the filter and reproduces the same filtered view in the new tab (shareable link).
B-06 | Donor | uat.donor@proximate.org | B-02 done | 1. Log in as the donor (fresh window). 2. Open the donor dashboard. | — | The new round 'UAT Round — July 2026 (Team)' is now visible to the donor automatically — because UAT Donor Foundation funds it. Round 8 is still there. Nothing else (no Blue Nile).
B-07 | OB | ob@proximate.org | B-02 done | 1. On round {R}, find the panel selection / community panel section. 2. Add candidate 'Halima Adam Koko' and upload UAT_Panelist_CV_Halima.pdf as her CV. 3. Generate/copy the public voting link. | UAT_Panelist_CV_Halima.pdf | Candidate saves with CV attached. A public voting link (token URL) is produced for community panel selection.
B-08 | Public voter | — incognito — | B-07 done | 1. Open the voting link from B-07 in an incognito window. 2. Cast a vote for Halima. 3. Try to vote a second time from the same link. | Voting token link | Vote page loads without login (Arabic/English available), vote is accepted and confirmed. A second vote from the same token is prevented or clearly handled per design — no double count.

## 3. Nomination & endorsement
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
C-01 | Partner (public) | — incognito — | None | 1. Open https://web-production-6f8a.up.railway.app/proximate-nominate/ in incognito. 2. Fill the self-nomination for 'Amal Relief Initiative (UAT)': location Ed Damazin, phone +249 91 000 0042, email uat.partner.amal@example.org, brief description 'UAT test nomination — community relief group'. 3. Submit. | Details from UAT_PIF_Amal_Relief.pdf | Form (available in Arabic and English) submits successfully and shows a confirmation. No login required.
C-02 | OB | ob@proximate.org | C-01 done | 1. Open https://web-production-6f8a.up.railway.app/proximate/admin/partners/. 2. Search 'Amal'. 3. Open the partner page and note its ID into 'Runtime values' as {P}. 4. Check the Due diligence tab. | Search: Amal | 'Amal Relief Initiative (UAT)' appears in the register as a nominated partner. Sanctions screening has already run automatically on self-nomination (a screening result is visible in DD).
C-03 | OB | ob@proximate.org | C-02, B-02 done | 1. Open round {R}. 2. Use Add partner and select 'Amal Relief Initiative (UAT)'. | Round {R}, partner {P} | Partner is attached to the round; the round page shows the partner with its current stage (auto-computed, human-readable — not a raw code).
C-04 | Endorser (public) | — incognito — | None | 1. Open https://web-production-6f8a.up.railway.app/proximate-endorse/ in incognito (public endorser sign-up). 2. Register 'UAT Endorser Omar', phone +249 91 000 0077, community Ed Damazin, set a password. 3. Submit. | Name/phone as in steps | Registration succeeds into a pending (light-KYC) state — the new endorser can NOT yet endorse. A clear message explains their application is being reviewed.
C-05 | OB | ob@proximate.org | C-04 done | 1. In the console, open the endorser approvals queue. 2. Find 'UAT Endorser Omar' — real name shown (not 'User #N'). 3. Approve via the explicit confirm step. | — | Queue shows the pending endorser with name and any screening flag. Approval requires a confirm step (not one accidental click). After approval the endorser leaves the queue.
C-06 | Endorser | fatima@amani.org / pass123 | C-03 done | 1. Log in as Fatima. 2. In the endorser inbox, choose 'Amal Relief Initiative (UAT)'. 3. Complete the 3-question endorsement wizard: answer by typing (e.g. 'UAT: known in the community, distributes aid fairly'), or record voice for one question. 4. Submit. | Answers prefixed 'UAT:' | The wizard is simple (3 questions, one per screen, works in Arabic). Submission confirms. The endorsement is recorded against Amal.
C-07 | OB | ob@proximate.org | C-06 done | 1. Open partner {P} → Endorsements tab. 2. Open Fatima's endorsement. | — | Endorsement detail shows the three answers (and a transcript if voice was used). The partner's endorsement count / reputation reflects the new endorsement.
C-08 | OB | ob@proximate.org | C-06 done | 1. Check the stage chip for partner {P} on the partners register and on round {R}. | — | Partner stage has moved forward from 'nominated' to an endorsed state, shown with a human label and consistent status colours (amber=waiting, green=done).

## 4. Due diligence
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
D-01 | OB | ob@proximate.org | C-02 done | 1. Open partner {P} → Due diligence tab. 2. In PIF intake, upload UAT_PIF_Amal_Relief.pdf and UAT_Registration_Certificate_Amal.pdf. 3. Fill/confirm the PIF fields (org name, registration no. UAT-REG-2019-0042, banking channel hawala 'Al-Baraka exchange (UAT)'). | UAT_PIF_Amal_Relief.pdf, UAT_Registration_Certificate_Amal.pdf | Files upload and are listed as PIF attachments. PIF fields save. Bank/payment details are visible here (OB-only surface) — they must NOT appear on any public or donor page later.
D-02 | OB | ob@proximate.org | D-01 done | 1. In DD, open the sanctions screening section for partner {P}. 2. Run/refresh screening. | — | Screening runs and records a result (clear expected for the fictional name). If the SAM.gov check has no API key configured, it must say so gracefully — no crash, no fake 'clear'.
D-03 | OB | ob@proximate.org | D-01 done | 1. In DD, open adverse-media verification. 2. Click the AI 'Run web check' to pre-fill. 3. Review the draft, set verdict Clear, save. | — | AI drafts a summary (may take ~10-30s). OB can edit before saving. Saved verification shows verdict + date. If AI is unavailable, a fallback notice appears and manual entry still works.
D-04 | OB | ob@proximate.org | D-01 done | 1. In DD, open leadership screening. 2. Add the three leaders from UAT_Leadership_List_Amal.pdf (Amina Yusuf Hassan — Director; Khalid Osman Abdalla — Finance; Sara Ibrahim Musa — Programme). 3. Screen/record a result for each. | UAT_Leadership_List_Amal.pdf | All three save with per-person screening results. The DD summary reflects leadership screening as completed.
D-05 | OB | ob@proximate.org | D-01 done | 1. In the partner's media verification section, upload UAT_Evidence_Photo_1.jpg. 2. Run the AI verification draft, then record an OB verdict. | UAT_Evidence_Photo_1.jpg | Photo uploads and previews. AI draft appears for review; OB verdict saves. Unverified media is clearly marked as unverified until the verdict.
D-06 | OB | ob@proximate.org | D-02..D-05 done | 1. Complete the vetting assessment for partner {P}. 2. Review the DD summary panel. | — | Vetting assessment saves. The DD summary shows each check (sanctions, adverse media, leadership, PIF, media) with a human status — the overall picture reads at a glance.
D-07 | OB | ob@proximate.org | D-01 done | 1. Open the FSP registry (Operations). 2. Add FSP 'Al-Baraka exchange (UAT)', type hawala. 3. On partner {P}, click Add disbursement method. FIRST try saving with fields empty. 4. Then fill: type hawala, FSP Al-Baraka (UAT), contact +249 91 000 0042 — save. | FSP + method details | Empty save is impossible — the Save button stays disabled (or shows required-field errors) until the mandatory fields are filled. With fields filled, the method saves and is listed on the partner.
D-08 | OB | ob@proximate.org | D-07 done | 1. Verify the partner's payment channel (bank/method verification action). 2. Note: if you try this BEFORE D-07's method exists, it must be blocked with a clear message. | — | Verification succeeds now a method exists, and the partner reaches a DD-clear / verified state with a green status. (The no-method attempt is refused with an explanation, not an error page.)
D-09 | OB (negative) | ob@proximate.org | Run BEFORE D-08 completes, or use another non-clear partner | 1. Try to create a disbursement for a partner that is not yet DD-clear (round {R} → new disbursement, or from the disbursements register). | — | Creation is blocked, and the why-blocked guidance says exactly what is missing (e.g. 'payment method not verified') with a link to fix it — not a bare error.
D-10 | OB | ob@proximate.org | Partners register has data | 1. On the partners register, set a status filter + a search term. 2. Click Save filter and name it 'UAT view'. 3. Clear filters, then re-apply from the saved chip. | Filter: any status + 'Amal' | The saved chip appears, persists on this device, and re-applies both the status and search in one tap. (Saved filters are per-device; up to 6.)

## 5. Disbursements
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
E-01 | OB | ob@proximate.org | D-08 done (partner {P} DD-clear) | 1. On round {R} (or partner {P} → Disbursements), create a disbursement: amount USD 4,500, purpose 'UAT tranche 1 — community response'. 2. Note its ID as {D1}. | USD 4,500 | Disbursement is created and automatically linked to the partner's verified payment method (the method is shown on the disbursement). Status: awaiting signature (human label).
E-02 | OB | ob@proximate.org | E-01 done | 1. Open disbursement {D1}. 2. Sign/approve it as ob@proximate.org. | — | Under the $10,000 threshold one OB signature is enough: status moves to disbursed/sent without requiring a second signer.
E-03 | OB | ob@proximate.org | E-01 done | 1. Create a second disbursement on round {R} for partner {P}: USD 12,000, purpose 'UAT tranche 2 — scale-up'. 2. Note ID as {D2}. 3. Sign it as ob@proximate.org. | USD 12,000 | Because it exceeds $10,000, one signature is NOT enough: after ob@ signs, status shows 'awaiting co-signature' (human label, amber).
E-04 | OB #2 | ob2@proximate.org / pass123 | E-03 done | 1. Still as ob@proximate.org, try to co-sign {D2} yourself. 2. Log in as ob2@proximate.org (second window) and co-sign {D2}. | — | The same person cannot provide both signatures — the co-sign control is unavailable/refused for ob@. ob2@ can co-sign, after which {D2} becomes disbursed.
E-05 | OB | ob@proximate.org | E-02 done | 1. On disbursement {D1}, locate the outcome/report sharing controls. 2. Click 'Copy outcome link' and check a WhatsApp share option exists. | — | Both controls exist; Copy puts a token URL on the clipboard. (Keep this link — sheet 6 uses the report link; the outcome link is used in F-07.)
E-06 | OB | ob@proximate.org | E-02 done | 1. On disbursement {D1} (or partner methods), record a Plan-B fallback: switch to the fallback FSP (Bank of Khartoum fixture) with reason 'UAT test — primary channel unavailable'. | Reason text as in steps | Plan-B is recorded and displayed as an amber advisory path on the disbursement — visible, auditable, and does not silently replace the original channel.
E-07 | OB | ob@proximate.org | Any time | 1. Open https://web-production-6f8a.up.railway.app/proximate/disbursements/. 2. Use the status filter chips and search. 3. Scroll/paginate if more than one page. | — | Register filters and paginates smoothly. Every status is a human label with the standard colours — never raw codes like pending_cosign.
E-08 | OB (read-only look) | ob@proximate.org | None | 1. Open https://web-production-6f8a.up.railway.app/proximate/disbursements/24/. 2. LOOK ONLY — do not click any action. | Disbursement #24 (QA fixture) | The flagged state renders as an amber warning card explaining the pause (outcome link and acknowledgement paused until re-verification). LEAVE IT FLAGGED — do not resolve.

## 6. Partner reporting
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
F-01 | OB | ob@proximate.org | E-02 done | 1. Open disbursement {D1}. 2. Copy the partner REPORT link (token URL). | — | A report token link is available for the partner. Copy succeeds.
F-02 | Partner (public) | — incognito — | F-01 done | 1. Open the report link in incognito (this is what a partner receives on WhatsApp). 2. Check the language toggle (Arabic default / English). 3. Type the narrative: 'UAT narrative — distribution completed for 120 households (fictional)'. 4. For a voice question, upload UAT_Voice_Note.wav (or record briefly). | UAT_Voice_Note.wav; narrative text | Page opens without login, is fully usable in Arabic, accepts typed answers and the voice file. (The tone clip may transcribe to nothing — acceptable; the file itself must attach.)
F-03 | Partner (public) | — incognito — | F-02 in progress | 1. Upload UAT_Evidence_Photo_1.jpg and UAT_Evidence_Photo_2.jpg as evidence. 2. Upload UAT_Evidence_Video.mp4. 3. Play the video back on the page. | 2 photos + 1 video from assets | All three upload with previews. The video streams/plays in the page player (seek works).
F-04 | Partner (public) | — incognito — | F-02, F-03 done | 1. Submit the report. | — | Submission succeeds and shows a clear acknowledgement/thank-you screen so the partner knows they are done.
F-05 | OB | ob@proximate.org | F-04 done | 1. Open disbursement {D1} again. 2. Review the submitted report: narrative, voice answer, photos, video. | — | Everything the partner submitted is visible to the OB: text, a working voice player, photo thumbnails and the playable video.
F-06 | OB | ob@proximate.org | F-05 done | 1. Check the verification state of the newly submitted media. | — | Fresh partner media is marked unverified until an OB verdict — it cannot flow to donor-facing surfaces while unverified.
F-07 | Partner (public) | — incognito — | E-05 done ({D1} outcome link copied) | 1. Open the outcome link from E-05 in incognito. 2. Complete the outcome attestation ('funds received / activity happened') with note 'UAT outcome — confirmed (test)'. | Outcome token link | Outcome page opens without login and records the attestation with confirmation. (This is the 90-day follow-up surface; in UAT it is reachable immediately.)
F-08 | OB + Partner | ob@proximate.org, then incognito | F-05 done. Use {D1} — NEVER #24 | 1. As OB, flag one item of {D1}'s report ('UAT flag — needs re-verification (test)'). 2. In incognito, reopen {D1}'s outcome link. 3. As OB, re-verify/clear the flag. 4. Reopen the outcome link. | Flag reason text | While flagged: {D1} shows the amber paused card and the outcome link is paused (clear message, no crash). After re-verification: the pause lifts and the outcome link works again.

## 7. Report package & donor
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
G-01 | OB | ob@proximate.org | Sheet 6 done | 1. On round {R}, create a report package for the period to date. 2. Note its ID as {PKG}. 3. Copy the partner package token link. | — | Package is created in a draft/collecting state with a partner token link for content collection.
G-02 | Partner (public) | — incognito — | G-01 done | 1. Open the package token link in incognito. 2. Review the evidence shelf (media from the reporting flow). 3. Answer any package voice/text questions with 'UAT package answer (test)'. 4. Submit. | Text answers prefixed 'UAT' | Partner-facing package page works without login, in Arabic and English; existing media appears on the shelf; answers submit successfully.
G-03 | OB | ob@proximate.org | G-02 done | 1. On package {PKG}, trigger the AI compile. 2. Wait for the background job (refresh after a minute if needed). 3. Review both the English and Arabic drafts. | — | Compile produces a readable narrative in English AND Arabic, grounded in the submitted content (mentions the UAT activities; no invented partners or numbers). Run once only.
G-04 | OB | ob@proximate.org | G-03 done | 1. Edit the draft: fix any wording, redact the phone number if it appears. 2. Set per-item donor visibility: mark most items donor-visible, but leave ONE item internal-only. 3. Set the SDG→USD exchange rate if prompted (use 1 USD = 601 SDG, UAT value). | Rate: 601 | Editing and redaction save. Each item shows an internal/donor-visible state. Amounts display with the entered conversion.
G-05 | OB | ob@proximate.org | G-04 done | 1. Review the safeguarding gate copy on the OB package page. | — | The operator page clearly explains items are internal until made donor-visible — this instruction copy is visible ONLY to OB (donor check comes in G-08).
G-06 | OB | ob@proximate.org | G-04 done | 1. Publish package {PKG}. | — | Publish succeeds with a confirm step; package state becomes published.
G-07 | Donor | uat.donor@proximate.org | G-06 done | 1. Log in as the donor (fresh window). 2. Open https://web-production-6f8a.up.railway.app/proximate/reports/ and open the new package for round {R}. | — | The donor sees the published package: EN/AR narrative, evidence gallery — but ONLY the donor-visible items. The one internal-only item from G-04 is absent.
G-08 | Donor (leak canary) | uat.donor@proximate.org | G-07 open | 1. On the donor package page, read all visible copy carefully. | — | NO internal operator copy anywhere — specifically the phrase 'internal until you make it donor-visible' (or similar instructions) must NOT appear. No bank details, no tokens, no partner phone numbers.
G-09 | Donor | uat.donor@proximate.org | G-07 open | 1. Download the PDF in English — open it. 2. Download/switch to the Arabic PDF — open it. | — | Both PDFs download branded (Proximate orange). The Arabic PDF renders real connected Arabic script, right-to-left (not disconnected letters or boxes).
G-10 | Donor | uat.donor@proximate.org | Logged in | 1. On the donor dashboard, review the round cards for round 8 and round {R}. 2. Toggle 'Receiving updates' (follow) off and on for round 8. | — | Cards are donor-grade (clean metrics, human zero-states like 'No reports yet' rather than dashes/NaN). The follow toggle persists across a page refresh.
G-11 | Donor (negative) | uat.donor@proximate.org | Logged in | 1. Try opening a package that belongs to a round this donor does not fund — paste https://web-production-6f8a.up.railway.app/proximate/reports/1/ (and /2/) into the address bar. | Direct URLs | If that package belongs to a subscribed round it may open; anything outside the donor's rounds returns access-denied/not-found — never another donor's content. No error page crash.
G-12 | OB | ob@proximate.org | G-06 done | 1. Open the activities editor on round {R} / package {PKG}. 2. Adjust one activity line ('UAT activity — water point check') and save. | Activity text | The approved activity schedule is editable by OB, saves cleanly, and the change is reflected on the package/round view.

## 8. Governance & transparency
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
H-01 | Public | — incognito — | None | 1. Open https://web-production-6f8a.up.railway.app/proximate-grievance/ in incognito. 2. Submit a grievance: 'UAT grievance — test entry, please triage as test'. Leave contact optional/empty. 3. Note the reference code. | Grievance text as in steps | Grievance form works without login (Arabic available), accepts anonymous submission, and returns a reference code on success.
H-02 | OB | ob@proximate.org | H-01 done | 1. In the console, open the grievances queue. 2. Find the UAT grievance and move it through triage (acknowledge / assign / set status) with note 'UAT triage (test)'. | — | The grievance appears with its reference; triage actions save and the status history is kept.
H-03 | OB | ob@proximate.org | Partner {P} exists | 1. On partner {P}, open the intervention register. 2. Create a low-severity intervention 'UAT intervention — documentation follow-up (test)'. 3. Check the response timer. | Intervention title as in steps | Intervention saves with an SoP-13 response timer (deadline computed from severity). It is listed on the partner with a clear status.
H-04 | Platform Admin | admin@kuja.org | Sheets 2-7 executed | 1. Open https://web-production-6f8a.up.railway.app/admin/audit-chain/. 2. Filter/scan for today's UAT actions (round created, disbursement signed, package published…). 3. Expand two rows. | — | Every significant UAT action from today appears in the chain with plain-language collapsed rows; expanded rows show hashes + payload. Report/vote/outcome tokens appear redacted (token:xxxx…).
H-05 | Platform Admin | admin@kuja.org | H-04 open | 1. Use the audit export (download) control. 2. Open the downloaded file in a text editor and spot-check 3 rows. | — | Export downloads (NDJSON/JSONL). Rows carry the proximate network stamp; no plaintext secrets or full tokens inside.
H-06 | Public | — incognito — | None | 1. Open https://web-production-6f8a.up.railway.app/proximate/ in incognito (public transparency page). | — | Page loads without login: aggregate figures only (envelope moved, rounds with title + trigger). No partner PII, no per-disbursement detail, no bank info. Arabic version available.
H-07 | OB | ob@proximate.org | Round {R} has activity | 1. On round {R}, use the end-of-round / round report CTA to generate the server PDF. | — | A branded round report PDF is generated and downloads; figures match the round's actual disbursements ({D1}+{D2} totals).
H-08 | OB | ob@proximate.org | Logged in | 1. Open https://web-production-6f8a.up.railway.app/settings/notifications/. 2. Review the category groups. 3. Toggle one category off, save, refresh, toggle it back on. | — | Preferences are grouped by category showing how many channels are on; toggles persist across refresh.

## 9. Cross-cutting UX
ID | Persona | Log in as | Precondition | Steps | Test data | Expected result | Result | Tester | Date | Notes / defect ref
I-01 | OB | ob@proximate.org | Logged in | 1. Narrow the browser to phone width (<640px) or open on a phone. 2. Visit the dashboard. 3. Tap each bottom-nav item. 4. Repeat the width check logged in as the donor and as Fatima. | — | At phone width the OB gets a 5-item bottom nav (Home, Rounds, Partners, Disbursements, More). Every item navigates; nothing overflows horizontally. Donor and endorser do NOT get this nav.
I-02 | OB | ob@proximate.org | Logged in | 1. Open https://web-production-6f8a.up.railway.app/settings/. 2. Review the hub: profile, language, theme, low-bandwidth, links to notifications/security. 3. Click Settings from the sidebar too. | — | One Settings landing page holds all preferences with role-appropriate extras (no marketplace tools on Proximate). All sidebar Settings links land here.
I-03 | OB | ob@proximate.org | Logged in | 1. In Settings, switch theme to Dark. 2. Visit dashboard, partner {P}, round {R}, a disbursement. 3. Switch back to Light. | — | Dark mode is legible everywhere visited: no white-on-white or invisible text, status colours still distinguishable.
I-04 | OB | ob@proximate.org | Logged in | 1. Switch language to Arabic (Settings). 2. Walk the dashboard, partners register, round {R}, and a disbursement. 3. Switch back to English. | — | Full RTL mirroring; Arabic labels on nav, buttons, statuses. Untranslated operator strings may exist (known gap — note WHERE you see English) but layout must never break.
I-05 | OB | ob@proximate.org | Logged in | 1. In Settings, open the language list. 2. Switch to Français, spot-check the sidebar, then return to English. | — | Six languages offered (EN, AR, FR, ES, SW, SO). French renders on the nav without raw translation keys (no 'proximate.xxx' strings).
I-06 | OB | ob@proximate.org | Logged in | 1. In Settings, enable low-bandwidth mode. 2. Open a media-heavy page (disbursement {D1} report). 3. Disable it again. | — | Toggle persists; with it on, heavy media is deferred/reduced and pages stay usable. No errors either way.
I-07 | OB | ob@proximate.org | Partners exist | 1. Open partner {P}, switch to the Due diligence tab. 2. Use the Next / Previous controls to step to the neighbouring partner and back. | — | Stepping moves through partners in the register's order and KEEPS the active tab (lands on the next partner's Due diligence tab, not Overview).
I-08 | Donor + OB | both accounts, same browser profile | Both logins available | 1. In one browser profile, log in as ob@proximate.org, open a report package page. 2. Log out via Settings. Log in as uat.donor@proximate.org WITHOUT clearing storage. 3. Open the same round's package from the donor side. | — | After the account switch the page renders donor copy only — no leftover operator wording from the cached OB session (this exact switch once leaked internal copy; it must stay fixed).

## Defect log
# | Date | Tester | Case ID | Severity (P1/P2/P3) | What happened (actual result) | Screenshot / file ref | Status